## Sheet1
ADVANCED PRODUCT QUALITY PLANNING
|  |  |  | PART NAME | PARTS | MODEL |  |  | 6
5
4
3
2
1
N
[9 empty] | No |  | Revision |  |  | DATE |  |  | APPROVAL
Year
| ITEMS |  |  |  |  | Term | JANUARY | FEBRUARY | MARCH | APRIL |  | MAY | JUNE |  | JULY |  | AUGUST
DETAIL
CUSTOMER |  | BASIC SCHEDULE |  | Vehicle Builds and Important Events
Evaluation of Design Target
|  | Program Planning & Definition |  | Consideration of Material & Component Supplier
Consideration of Process Flow
Product and Process Special Characteristics
Drawing Submission
Evaluation Result Submission
Trial Build Parts Delivery
Design Review
Subcontractor Selection
|  | Product Design and Development |  | Protoype Control Plan
Consideration of Tooling, Equipment and ProcessFlow
Review of Product / Process Characterisitcs
PIC
|  |  | Target Requirements | Confirm Customer Quality Requirements
Confirm Customer Specifications
I |  |  |  | Pre-Launch Control Plan
N |  |  | Advanced Quality Planning | PFMEA Draft
T |  |  |  | Past Defect History & C/M
E |  |  |  | Functional & Performance Analysis
R |  |  | Evaluation and | Reliability & Durability Analysis
N |  |  | Follow-up | Product Capability
A |  |  |  | Attendance at Trial Events
L |  |  |  | Team Feasisbility Commitment
|  | P |  | Product / Process Checklist
P |  | R | Process Design and | Floor Plan Layout
R |  | E | Development | Equipment Schedule
E |  | - |  | Subcontractor Part Submissions
P |  | P |  | Manpower Planning
A |  | R |  | Associate Training
R |  | O | Standardization | SOP , PCS and Mfg Standards
A |  | D |  | Packaging
T |  | U |  | Checking Fixtures
I |  | C |  | Mass Production Trial
O |  | T |  | Measurement System Evaluation
N |  | I |  | Process Capability
|  | O | Product / Process | PFMEA
|  | N | Validation | Process Verification
Product Validation Testing
|  | S |  | Production Control Plan
|  | T |  | Customer Submission (PPAP/ISIR/DLS)
|  | A |  | Support for Lineside Operations
|  | G |  | QA Inspection
|  | E | Feedback, Assessment and | Management Approval
|  |  | Corrective Action | Consideration of Continuous Improvement
[11 empty] | Planned Event |  |  |  |  | Completed Event

## Sheet2
12 | 96/1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 97/1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 98/1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 1